## Instructions
Project Security Plan (PSP) - Cybersecurity integration into projects -
Objectives of the PSP | Ease the integration of Security by design into projects, to support all Business needs: 1) To ensure security requirements and actions related to new business are effectively implemented. 2) To formalize security decisions/arbitrations during the project.
PSP owner during a project | Project Manager (or Proposal Owner in the PROPOSAL phase)
PSP template owner | Cybersecurity GRC team
Minimum confidentiality level once completed | RESTRICTED
Instructions
Who is responsible for completing and managing the Project Security Plan (PSP)? 1. PROPOSAL OWNER is responsible to fill it during the proposal phase. 2. As the project progresses, PROJECT MANAGER is responsible to fill the PSP. ------------------------------------------------------------------------------------------------ When to fill in the PSP? => From the start of the project, when the business need is formalized, and the project process starts. Firstly, the "Project information" tab needs to be filled. Then at each phase of the project (PROPOSAL, DESIGN, DEVELOP and DEPLOY phases), the responsible person must fill each field of the corresponding tab. Please NOTE that at each phase, the project's Security Advisor must be involved for approval. ------------------------------------------------------------------------------------------------ How does this document work? => The purpose of this document is to integrate Security by Design to support all Business projects. The PROPOSAL phase is the phase where the business needs and cybersecurity topics are gathered (Confidentiality, Integrity, Availability levels, regulation associated with the business need, exposure and hosting). Some basic cybersecurity controls are also performed. The DESIGN phase is the when the expected response to the business needs is designed. From high level (High Design) down to more details (Low Design). The DEVELOP phase is when the builds are performed. The focus here is on development security controls. The DEPLOY phase is the last step of the project before steady state mode. It focuses on cybersecurity controls (compliance controls, vulnerability controls and operational documents).
------------------------------------------------------------------------------------------------ Who is the first Cybersecurity interlocutor for my project? The Business Information Security Officer (BISO email team: biso@test.com) can guide the Product Owner through the first step of the project. Then, a Security Advisor will help the Proposal Owner and the Project Manager with cybersecurity throughout the progress of the project. He will check the information and verify that the actions associated with the PSP are properly managed. He will involve other cybersecurity teams when necessary. ------------------------------------------------------------------------------------------------
Where should I deposit the Project Security Plan (PSP) to share it with Cybersecurity teams?
Before sharing it, please add your project name to your PSP file name.
Go to the "Project Security Plan" dedicated page on the Cybersecurity Compass SharePoint: |  | CLICK HERE
If you don't have access to this Cybersecurity SharePoint or no right to drop it in, you can send it to the following Security Advisor team email box : advisor@test.com
------------------------------------------------------------------------------------------------ Remarks:
All the fields highlighted in light gray must be filled :
Notice: all fields in a red frame represent the cybersecurity result of the phase, or the most important things for cybersecurity. Those fields must be completed by the Project Manager (PM) following instructions from the Security Advisor
------------------------------------------------------------------------------------------------ Other contacts: * Data Governance team (will guide you in data classification): data@test.com * Security Operation Center (SOC) team (involved into log management, SIEM, etc.): soc@test.com * Application Security team (source code security, vulnerability scans, pentest, etc.): appsec@test.com * OT cybersecurity expert (for Operational Technology (OT)): ot@test.com * Cloud Security team (Cloud environments): cloud@test.com * CMA CGM group Data Privacy Officer (regarding Personal Information regulation): dpo@test.com * HO Network team (IP addresses, subnetworks, etc.): network@test.com
------------------------------------------------------------------------------------------------ Frequently Asked Questions - FAQ:
Where can I find further information (stakeholders or required documents) about Cybersecurity in projects? E.g., guidelines for Cryptography Standards, Secure Coding , Proof of Concept, Decommissioning
Go to the "Cybersecurity requirements in projects" dedicated page on the Cybersecurity Compass SharePoint: |  | CLICK HERE
------------------------------------------------------------------------------------------------ During the PROPOSAL phase of the project, what are the most frequently applicable regulations/laws/standards related to cybersecurity?
- Personal Information regulation (GDPR, California Consumer Privacy Act (CCPA), etc.) - NIS-OES (Operators of Essential Services) ("NIS-OSE" in French), when the project deals with: * Transport Planning (Planification des trajets) / * Dangerous Goods Shipping (Transport de marchandises et de matières dangereuses) / * Vessel Maintenance (Maintenance des navires) - IMO regulation: the International Maritime Organization (IMO) has published a document with Cyber requirements (Guidelines on Maritime Cyber Risk Management). - DoD regulation (US Department of Defense): some entities have contracts with the US DoD via US Transportation Command and Voluntary Intermodal Sealift Agreement (VISA). As part of US Government Contracts, these entities offices and their applications and Infrastructures must be compliant to Protecting Controlled Unclassified Information (CUI) in Non Federal Information Systems and Organizations (NIST SP 800-171). - SWIFT's Customer Security Program (treasury operations)
------------------------------------------------------------------------------------------------ During the DEPLOY phase of the project, how can I trigger a Penetration testing (Pentest)? Via the "PENETRATION TEST REQUEST FORM" on End User Portal (EUP*) Notice: in case of SaaS solutions, take into consideration the following information: 1 - The SaaS provider shall provide a proof of a recent penetration testing performed by a 3rd party 2 - If the supplier doesn’t have such evidence and cannot get one, Cybersecurity (via Application Security team) can organize a pentest for them done by a 3rd party, but the price of the assessment will be backcharged to them / deducted on the contract How to request a corporate Web Application Firewall (WAF) configuration? Via the "WAF PROFILE CONFIGURATION" request on End User Portal (EUP*)
* EUP requests in Service Now: |  | CLICK HERE
------------------------------------------------------------------------------------------------ GLOSSARY: Pre-risk assessment: a cybersecurity activity that decides if the solution will require a complete risk assessment TPRM - Third-Party Risk Management: a cybersecurity process assessing the maturity level in cybersecurity of a supplier, prior to contract. Only the Security Advisor can trigger the TPRM process ISRA - Information Security Risk Assessment: a cybersecurity process evaluating the risks of a solution SAST - Static Application Security Testing: an IT activity to detect potential vulnerabilities in code written in house SCA - Software Composition Analysis: a cybersecurity activity allowing to detect components with known vulnerabilities Container image scanning: a cybersecurity activity allowing to detect vulnerabilities in container images DAST - Dynamic Application Security Testing: a cybersecurity activity to detect vulnerabilities in an application before it goes Live Vulnerability scan: detection of known vulnerabilities in an application or an infrastructure before it goes Live or is updated Penetration testing (aka "Pentest"): a test simulating a real attack performed by an cybersecurity expert to detect - known or unknown - vulnerabilities

## Project information
Project Security Plan (PSP) - Project information
Project Summary
Project Name |  | MAIA
Project Legal entity |  | Project Legal Entity
RFS (Request For Service) Code (if existing): |  | TEST-12345
Business activity/domain (e.g., Shipping, Finance, HR department, Logistics, etc.) |  | Transversal
Project Functional Description Short description of the purpose of the project: - Business needs - Type (application creation/update, infrastructure, etc.) - Scope (only one specific business, transversal across entities, strictly IT, etc.) - End users |  | R1 SCOPE MAIA is an in-house solution inspired by ChatGPT, designed to optimize and enrich the employee experience. This is a version of ChatGPT hosted in a protected environment. In this way, we avoid the risk of publicly disclosing sensitive data outside the Group. MAIA's main features: Translate texts in any language Synthesize documents Search for information interactively on loaded documents Ask questions about the Group's CSR strategy Generate images and texts according to themes Web search Voice transcript C-Park booking Business Topics MAIA Back Office Topic : VAS Bot
Name of the application that will be released or upgraded (if already defined) |  | N/A
Project Stakeholders
Business Owner (Product Owner) |  | Person Placeholder
Product Manager (IT) |  | N/A
Proposal Owner (person responsible of managing the proposal phase) |  | N/A
Project Manager |  | Project Manager
Data Governance Officer
Solution Architect |  | Solution Architect
Business Information Security Officer (BISO)
Security Advisor |  | Security Advisor
other cybersecurity contributors* (Cyber PMO, Security Architect, Cloud Security, etc.) |  | Other contributors
* : if relevant

## PROPOSAL phase
What is the level of Internet exposure?
| Project Security Plan (PSP) - PROPOSAL phase |  |  | VERY HIGH: full Internet exposed
HIGH: no filter IP address WITH for user authentication : Multi-Factor Authentication (MFA) or CMA CGM Identify Federation
| PROPOSAL phase results (restricted to Security Advisor) |  |  |  | MODERATE: CMA CGM IP addresses restriction with login/password
LOW: no exposure, OR via a dedicated VPN (Virtual Private Network), OR via a dedicated network link, OR via CMA CGM IP addresses restriction with MFA or with CMA CGM Identify Federation usage
Pre-risk assessment result
Cybersecurity remarks regarding this phase
| Critical asset involved (automatic field) |  | YES
| Control indicator |  | THANK YOU, ALL REQUIRED INFORMATION HAS BEEN PROVIDED
Confidentiality, Integrity and Availability (CIA) Classification
1) Contact Data Governance office to correctly classify the data
2) Report the result in the table below
| Confidentiality |  | 4 - Confidential
| Integrity |  | 2 - Moderate
| Availability |  | 1 - Low
Comments
Applicable regulations/laws/standards (to be checked with your BISO)
| Is there Personal Data? |  | Yes
If yes, please contact your DPO for compliance aspects
| Indicate the regulations, laws or standards that apply to this project |  | Personal Information Regulations (GDPR-CCPA-etc)
Others (if any)
Exposure & Hosting
| Is the application exposed on the Internet? |  | No
| Are there interactions with systems? |  | Yes
| Is there any communication planned with a third-party? |  | No
| What is the planned hosting model? |  | External (PaaS)
| Where will the data be hosted? |  | Azure Tenant
Additional questions
Cybersecurity Topic | Other questions: | Answers | Comments
Third Party Risk Management | Does the project involve a new contract with one or more suppliers? | No
If yes, initiate the TPRM Process
| Does the project go through a Request For Proposal (RFP)? | No
If already identified, what is the name of the supplier(s)?
Physical assets (OT, IoT, etc.) | Does the project include systems that interact with the physical environment? (e.g., Operational Technology (solution in ships, UAV*, SCADA*, etc.), Internet Of Things (CCTV*, etc.). | No | Consult existing specifications: (if compliant, go, if not, consult OTCS team)
Authentication and user access management | Is the project solution compatible with corporate Identity Tools? | Yes | AzureAD SSO + SAP business role
Secrets Management | Are you integrated with corporate vault solution? Yes/No If not, how do you manage passwords? | YES | Azure Key vault

## Low DESIGN phase
Project Security Plan (PSP) - DESIGN phase - second part (Low DESIGN)
DESIGN phase results
Cybersecurity remarks regarding this phase
Cybersecurity Topic | Cybersecurity Requirements | Answers | Mandatory/Optional | Special Cases | Functional architecture diagram (only if different from High DESIGN tab:
Authentication and access rights management (Identity and Access Management: IAM) | Describe the identification and authentication management solution. | Utilisation du SSO + SAP business role MFA …. | Mandatory
| Describe the solution used for the integration with the Enterprise Identity Federation (Single Sign-On - SSO) Mandatory for administrators accounts and others accounts that access ""Restricted"" or ""Confidential"" data confidentiality level" | Federate Azure AD | Mandatory
| Describe the Multi Factor Authentication (MFA) solution supported by the solution | Microsoft Authenticator | Mandatory
| Please describe how users will be provisioned. | SAP IDM | Mandatory
| Describe the access rights management in the solution. | SAP IDM: 3 business roles Standard, Advanced, IT | Mandatory
| Indicate the user session time out (i.e., inactivity time before disconnection). | Standard Azure AD timeout | Mandatory
| Describe how Service accounts are managed. | N/A | Mandatory
Impact analysis on systems | Describe the interactions with other systems (System Context Diagram). | N/A | Mandatory
Antivirus & Endpoint Protection | Indicate if the application is expected to be compatible with the corporate Endpoint Detection & Response (EDR). If existing, describe exclusions (e.g., directories, databases, etc.). | N/A (kubernetes containers) | Mandatory
| If the project solution does not use corporate EDR, describe the implementation of the endpoint protection solution. | N/A (kubernetes containers) | Mandatory
Secrets Management | Indicate the corporate solution used to manage secrets (CyberArk or HashiCorp Vault). If not applicable, describe how secrets are managed. | AWS Secret manager | Mandatory
Solutions components/configuration | Provide the name and version of the components used by the solution (e.g., Microsoft IIS, Content Management System (CMS), Apache, Database, etc.). | Kubernetes node js react EKS Azure backend MongoDB | Mandatory |  | Technical architecture diagram (if different from HLD part):
Administration Security | Describe how the privileged accounts (administrators, etc.) have access to the solution (e.g., rebound platform, MFA authentication, secured protocols (SSH V2, RDP over TLS≥1,2, SSL VPN, HTTPS dedicated administration panel, etc.), dedicated administration network, etc.). | ADM accounts managed by PUMA Azure admin portal (HTTPS) AWS admin portal (HTTPS) | Mandatory
Patch Management | Is there a patch management process? If yes, who is responsible? If no, how is patch management addressed? | Full PaaS on Azure (no patch management) CTO / EKS Platform Team (Squad Service) for AWS | Mandatory
Actions logging and SOC integration | Provide details on logs exporting capabilities (e.g., network, files, etc.). | Cloud Watch & Cloud Trail collect automatically the logs for the INFRA | Mandatory
| If the solution includes network equipments, can logs contain FQDN? Is there any FQDN size limitation? | Dérogation : | Mandatory
| If the solution includes network equipments, is the network port customizable? | Dérogation : | Mandatory
| Please indicate if the log format is customizable. If yes, how? | Dérogation : | Mandatory
| Please detail legal retention periods (if any). | Dérogation : | Mandatory
Cryptography | Describe the implementation of the cryptographic controls (e.g., certificates, TLS, SSH configuration, encryption algorithm versions used, etc.). | Native encryption on EKS For Mongo, encryption as well : AES 256 | Mandatory
| Does the solution/application use TLS certificates issued from a public CA (Certificate Authority)? If so, which authority? | Internal PKI | Mandatory
Secured Development | If any, is external (i.e., vendors) source code digitally signed? If not, provide justification. | N/A | Mandatory |  | Network flows matrix (if different from HLD part):
Network flows | Provide the network flows (including user access and other flows, IP source, IP destination, Port, Protocol) in the dedicated frame on the right side of this Excel sheet. If existing, please indicate the version of the flows matrix file/Integration File. | N/A | Mandatory
Resiliency | Describe implemented high availability mechanisms*. *: mandatory in case of "High" or "Very High" data availability level | Several pods on the EKS | Mandatory
Hardening | If default configuration elements (e.g., accounts, certificates, passwords, etc.) are not deleted, changed or renamed, please provide detailed justification. | N/A | Mandatory
Cloud Assessment | In case of Cloud solution hosted in an existing IaaS/CaaS platform*, please describe: - security group; - storage (S3 bucket or Blob) and related access policies; - encryption model (in transit and at rest); - WAF** solution and filtering configuration (baseline, etc.); - interconnectivity with external third parties. * : AWS Landing zone, Azure tenant, or ANL Cloud ** : Web Application Firewall | Dérogation : | Mandatory
Operational Technology (OT/IoT) | Describe all cybersecurity measures that are put in place to comply with the relevant OT/IoT standard (by default IEC 62443 or NIST SP800-82) | N/A | Mandatory
| ONLY for information, in case of and if existing, provide the name of the Low Level Design (LLD) project document and link to this document repository* where come from this information: * : not a directly link to the document, but the repository. Provide this information is not a substitute for completing this PSP document | link | Optional

## High DESIGN phase
Project Security Plan (PSP) - DESIGN phase - first part (High DESIGN)
Cybersecurity remarks regarding this phase
Third-Party Risk Management - TPRM (if performed) - supplier security assessment result
Name of the selected supplier
Cybersecurity Advice report result for the selected supplier
Recommendations/action plan (if existing)
Risk assessment (if performed) result - Information Security Risk Assessment (ISRA)
Status of the ISRA
ISRA – Color of highest residual Risks
Action plan defined?
| What type of solution is it? (automatic field: E43 in PROPOSAL phase) |  | Azure tenant CMA CGM (France)
| Which profile applies to your project solution? |  | Profil 3
Cybersecurity Topic | Cybersecurity Requirements | Answers | Comments | Mandatory/ Optional | Special Cases | Functional architecture diagram:
Architecture | Please copy/paste the functional and the technical architectures in dedicated frames on the right of this Excel sheet | Done |  | Mandatory
| Is the project solution compliant with best cybersecurity Architecture practices (DMZ, 3-tier architecture, etc.)? | Yes | AWS Landing Zone. Digital EKS Network and digital account | Mandatory
Please provide remediation plan
Please explain why in comments
Authentication and user access management (Identity and Access Management: IAM) | Is the project solution compliant with corporate Identify and Access Management - IAM - requirements*? * : IAM policy can be found in the Cybersecurity Compass SharePoint and apply to affiliates | Yes | Utilisation du SSO + SAP business role MFA …. | Mandatory | Please provide derogation
Please explain why in comments
Is a remediation plan provided?
Administration cybersecurity | Is administrators authentication compliant with the corporate IAM policy? | Yes | ADM accounts managed by PUMA | Mandatory
Please explain why in comments
| Is the project solution integrated with the corporate Privilege Access Management - PAM - solution? | Yes | Managed by PUMA + ZSCALER | Mandatory
Please explain why in comments
| Does the project solution use the corporate administrative solution to enforce secure communication protocols? Examples: SSH V2, RDP over TLS≥1.2, IPsec or SSL VPN, HTTPS dedicated administration panel, etc. | Yes | HTTPS | Mandatory
Please explain why in comments
Impact analysis on ecosystem | Are there any interactions with other systems (System Context Diagram)? | Yes | MongoDB Atlas | Mandatory
| What are the potential impacts: - Performance impact? - Load impact? - Availability Impact ? | No
Antivirus & Endpoint Protection | Are all the project solution endpoints (workstations, mobile devices and servers) protected by an anti-malware solution? | Not Applicable | EKS | Mandatory
| Please explain why in comments |  |  |  |  | Technical architecture diagram:
| If applicable, does the project solution emails gateway apply filtering features (IP/Email@ blocking, files extensions whitelisting, etc.) and implement an anti-malware solution? | Not Applicable |  | Mandatory
Please explain why in comments
Secrets Management | Do you use a secret management solution? | Yes | Azure Key vault | Mandatory
Please explain why in comments
Actions logging and Security Operation Center (SOC) integration (if needed, cf. "Instructions" tab to find SOC team email contact) | Did you perform a workshop with SOC (Security Operation Center) team? | Yes |  | Mandatory | Please organize it before going ahead
| Is SOC integration capabilities possible? | Yes | Yes, in progress. Derogation to create (Derogation number : ) | Mandatory
| Are the SOC requirements taken into account in the architecture (e.g. dedicated equipment, flows to the SIEM/SOC infrastructure, etc.)? | Yes |  | Mandatory
Cryptography | Are all the certificates provided by an approved certification authority? | Yes | Internal PKI | Mandatory
| Will the corporate cryptography Standard* be enforced? * : standards can be found in the Cybersecurity Compass SharePoint and apply to all affiliates | Yes |  | Mandatory | Please provide derogation
Secure Development | Have you performed a workshop with "Application Security" team? | Yes | DAST conducted: green | Mandatory
Please explain why in comments
Cf. "Secure coding guidelines" for developers in the "Cybersecurity requirements for projects" page on the Cybersecurity compass SharePoint:
Regulations impacting cybersecurity | Did you take into account the impacts of regulation on the architecture? (detail the results) | Yes | DPIA done for Pilot phase (R1) For global deployment: In progress with DPO, regulation by countries | Mandatory
Network flows | Are the sub-networks logically and/or physically segmented based on criteria such as business needs, technologies, locations... (Examples of common VLANs: Office/Users, Wi-Fi, ToIP, Printers, Administrators)? | Not Applicable | PAAS | Mandatory
Please explain why in comments
| Are network flows encrypted? | Yes | HTTPS | Mandatory
| Please explain why in comments |  |  |  |  | Network flows matrix:
| Is a corporate* WAF (Web Application Firewall) integrated to the design? | Not Applicable | Not exposed on internet (using ZPA) (for Pilot phase - R1)
| Will you perform corporate* WAF (Web Application Firewall) testing on a non-production environment? | Not Applicable
Further info: - contact HO Network Team for VIP configuration - EUP request for "WAF profile configuration" * : for On-Premise, and existing IaaS/CaaS platforms (AWS Landing zone,Azure, etc.)
Data protection | Are secure encryption (at rest and in transit) capabilities* planned? * : mandatory for "Restricted" or "Confidential" data | Yes | MongoDB Atlas, active by default Encryption at application level | Mandatory
Please explain why in comments
| In case of sensitive personal data, does the solution provide anonymization/pseudonymization capabilities? | Yes | Hidden usernames | Mandatory
Please explain why in comments
Reversibility | Does the solution use data types that are broadly compatible with industry standards* (to ensure interoperability)? Example: database management system (DBMS), results files, configuration files, etc. | Not Applicable |  | Mandatory
Please explain why in comments
Resiliency | Are the backups encrypted? | Yes | MongoDB backups encrypted | Mandatory
Please explain why in comments
| Indicate the Recovery Time Objective (RTO) and Recovery Point Objective (RPO) of the solution |  | RTO > 48h RPO > 48h | Mandatory
Cloud Security | Is the solution compliant with the corporate "Cloud Security Standard"? * : standards can be found in the Cybersecurity Compass SharePoint and apply to all affiliates | Yes | Using Azure tenant AWS Landing Zone | Mandatory | only for Outsourcing projects
Please explain why in comments
Operational Technology (OT) | Does the project involve operational technology (OT)? | No |  | Mandatory | only for Operational Technology (OT)
| Have you contacted an OT cybersecurity expert? |  |  | Mandatory | Please organize before going ahead
| Did you take into account the impacts in the architecture? |  |  | Mandatory | only for Operational Technology (OT)
| For information, please provide the name of the High-Level Design (HLD) project document and link to its repository* *: not a direct link to the file, but only to the repository/folder. Provide this information is not a substitute for completing this PSP document |  | wiki | Optional
Note on C21: INDICATIONS: Profile 1 - Critical applications: - One of the CIA score (ref. Asset management standard) reach 4 or when the sum of each CIA score reach 8 - The application is under the NIS-OES regulation (identified as Essential Information System) Profile 2 - Exposed to external parties (the application is exposed to Internet or exposed to private external parties as customer, partner, API included) Profile 3 - Non-exposed and non-critical applications: all other applications WARNING : in case of SaaS deployments, take into consideration the following information: 1 - The SaaS provider shall provide a proof of a recent penetration testing exercise done by a 3rd party provider 2 - If the supplier doesn’t have such evidence and no idea who to work with, CMA CGM Cybersecurity (via Application Security team) can organize a pentest for them done by a 3rd party, but the price of the assessment will be backcharged to them / deducted on the contract
Note on I41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Detail the Azure part: Azure APIM gateway, subscribtion, authentication, Application Gateway etc...
Note on E70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please update RTO & RPO from HLD

## DEVELOP phase
Project Security Plan (PSP) - DEVELOP phase (applicable only if source code is produced for CMA CGM)
DEVELOP phase results (only if source code is produced for CMA CGM)
Cybersecurity remarks regarding this phase
Secure Coding Controls (only if source code is produced for CMA CGM)
Software Composition Analysis (SCA)
Status of the test | Not Applicable
Result (number of critical vulnerabilities)
Are there any remaining critical vulnerabilities?
If yes, is the derogation provided?
Static Application Security Testing (SAST)
Status of the test | Not Applicable
Result (number of critical vulnerabilities)
Are there any remaining critical vulnerabilities?
If yes, is the derogation provided?
Containers image scanning (if containers used)
Status of the test | Done
Result (number of critical vulnerabilities) | 0
Are there any remaining critical vulnerabilities? | No
If yes, is the derogation provided?

## DEPLOY phase
Project Security Plan (PSP) - DEPLOY phase
DEPLOY phase results
Cybersecurity remarks regarding this phase
Compliance with regulations
If the project is subject to regulations impacting cybersecurity (e.g., GDPR, NIS-OES, US DoD, etc.), what is the state of compliance check? | Done
If the state of compliance is "To do" or "Ongoing", please explain why and what is the action plan associated.
For NIS-OES regulation, did you receive the NIS-OES accreditation?
Security vulnerability controls WARNING: in case of SaaS application, take into consideration the following information: 1 - The SaaS provider shall provide a proof of a recent penetration testing exercise done by a 3rd party provider 2 - If the supplier doesn’t have such evidence cannot get one, Cybersecurity (via Application Security team) can organize a pentest for them, executed by a 3rd party, but the price of the assessment will be backcharged to them / deducted on the contract.
Vulnerability scan (not required for SaaS application)
Status of the test | Not Applicable
Result (number of critical vulnerabilities)
Are there any remaining critical vulnerabilities?
If yes, is the derogation provided?
Dynamic Application Security Testing (DAST) (not required for SaaS application)
Status of the test | Done
Result (number of critical vulnerabilities) | 0
Are there any remaining critical vulnerabilities? | No
If yes, is the derogation provided?
Penetration testing
Status of the test | Done
Result (number of critical vulnerabilities) | 0
Are there any remaining critical vulnerabilities? | No
If yes, is the derogation provided?
Information cybersecurity audits (organizational and physical audit, architecture audit, configuration audit, etc.)
Status of the test | Not Applicable
Result (number of critical vulnerabilities)
Are there any remaining critical vulnerabilities?
If yes, is the derogation provided?
Cybersecurity controls in operational documents (not required for SaaS application)
Did you fill the operational document (including cybersecurity requirements)? | Yes
Did you fill the installation document (including cybersecurity requirements)? | Not Applicable
Did you release a decommissioning procedure (including cybersecurity requirements*)? *: see cybersecurity expectation in the "Decommissioning guidelines" document in the "Cybersecurity requirements in projects" page on the Cybersecurity Compass SharePoint (link in the "Instructions" tab). | Not Applicable
Note on C50: The security requirements expected to be into a dedicated security management chapter in the operational document are: - Indicate the operational contact list (Business owner, Data owner, etc.) - Describe the account/access and rights management during the life of the solution - Describe the procedure to perform the vulnerability management (operational contact, security process to follow, cybersecurity contacts to reach, etc.): - Describe the procedure to perform the patch management (classification, prioritization, security process to follow, cybersecurity contacts to reach, etc.): - Describe the procedure to perform the change management (action to perform, prioritization, process to follow, change contact to reach, etc.): - Describe the procedure to manage security incident (classification of the incident, prioritization, security process to follow, cybersecurity contacts to reach, etc.) - List all assets (name, type, version, IP addresses) and confirm that theirs declarations have been done in the operational tools or database (TheKEY, etc.) - Indicate tools for monitoring the solution (availability): - Describe how the logs are sent to the SIEM tool and managed by the SOC (Security Operation Center) team:
Note on C51: The security requirements expected to be into the installation document are: - install an update and supported version - delete default configuration of the application - default editor/constructor accounts must be deleted or if not possible modified or renamed or if not possible at least password associated must be changed - default editor/constructor certificates must change - if application editor hardening exist, apply it - actions for decommissioning : uninstall application, delete accounts and accesses, delete network flows, wipe data with security methods, unplug the equipment concerned, etc.

## Classification Matrix
Confidentiality |  | Integrity |  | Availability
Label | Description | Label | Description | Label | Description
Confidential 4 | Assets must be classified as Confidential when the unauthorized disclosure, alteration or destruction of that data could cause a grave level of risk to affiliates. The highest level of security controls must be applied to Confidential data. Their compromise would: • be contrary to the group's financial interests • could cause significant financial, economic and commercial damage to the group • damage the group image • lead to the cessation or disruption of activities within the group • breach the confidentiality of personal data (HR, medical, etc.). Information that some people would consider to be Personal is included in this classification. E.g : Passwords, Financial data, personal data, Strategic plans, Credit card numbers. | Very High 4 | A business process utilising this data does not allow any (integrity) alteration. The unauthorized alteration or destruction of information could be expected to have a catastrophic adverse effect on organizational operations, organizational assets, or individuals. | Very High 4 | RTO =<4h00 (Group 0&1)
Restricted 3 | Assets must be classified as Restricted when the unauthorized disclosure, even to internal users and third parties, alteration or destruction of that data could result in a major level of risk to affiliates. An elevated level of security controls must be applied to restricted assets to ensure that only authorized persons/applications can access and manipulate them. E.g : Archticetures, Technical docs, Detailed system configurations, Vulnerability scans reports, network diagram | High 3 | A business process utilising this data allows very few (integrity) alteration. Protection of integrity is absolutely essential. Alteration or destruction of this data can cause serious direct or indirect damage. | High 3 | RT0 <= 24h00 (Group 2)
Internal 2 | Assets must be classified as Internal when the unauthorized disclosure, alteration or destruction of that data could result in a moderate level of risk to affiliates. By default, all Institutional Data that is not explicitly classified must be treated as Internal. A reasonable level of security controls should be applied to Internal data. E.g : Internal notes, System documentations, end user documentation | Moderate 2 | Business process utilising this data allows many (integrity) alteration. Security on a basic level is required. alteration or destruction of this data can cause direct or indirect damage. | Moderate 2 | OR RT0 <= 48h00 (Group 3)
Public 1 | Assets must be classified as Public when the unauthorized disclosure, alteration or destruction of that data would result in little or no risk to the affiliates. While little or no controls are required to protect the confidentiality of Public data, some level of control is required to prevent unauthorized modification or destruction of Public data. | Low 1 | The data may be altered. No extra protection of integrity is required. Integrity mistakes results have no consequential damage. | Low 1 | RTO > 48h00